| Activity | Predecessor | Optimistic Time (O) | Most Likely Time (M) | Pessimistic Time (P) | Expected Time (ET) |
| --- | --- | --- | --- | --- | --- |
| Project Kickoff & Charter Approval | None | 1 day | 1 day | 1 day | 1 day |
| System Architecture Finalized | Project Kickoff & Charter Approval | 8 days | 10 days | 12 days | 10 days |
| App Interface Design Complete | System Architecture Finalized | 9 days | 11 days | 14 days | 11 days |
| Data Aggregation Module Ready | System Architecture Finalized | 8 days | 10 days | 12 days | 10 days |
| Backend Development Complete | Data Aggregation Module Ready | 8 days | 10 days | 12 days | 10 days |
| NLP Detection Engine Complete | Backend Development Complete, Data Aggregation Module Ready | 8 days | 10 days | 12 days | 10 days |
| Fact-Checking API Integration | NLP Detection Engine Complete, Backend Development Complete | 8 days | 10 days | 12 days | 10 days |
| System Integration Complete | Fact-Checking API Integration, NLP Detection Engine Complete | 8 days | 10 days | 12 days | 10 days |
| Dashboard & Analytics Finalized | System Integration Complete | 9 days | 11 days | 13 days | 11 days |
| System Testing Complete | Dashboard & Analytics Finalized, System Integration Complete | 13 days | 15 days | 17 days | 15 days |
| Beta Pilot Launch | System Testing Complete | 8 days | 11 days | 13 days | 11 days |
| Operator Training & User Onboarding | Beta Pilot Launch | 12 days | 14 days | 16 days | 14 days |
| Marketing & Awareness Campaign Launch | Operator Training & User Onboarding | 8 days | 10 days | 12 days | 10 days |
| Full Deployment | Marketing & Awareness Campaign Launch | 9 days | 11 days | 13 days | 11 days |
| Project Closure | Full Deployment | 8 days | 10 days | 12 days | 10 days |